## Recap
First name | Last name | Trigramme | Year | Work tasks | Team tasks | Effectifs
Frame | [5 empty] | 1A | 22
Camille | Simon | CSN | 1A | 0 | 0 | 2A | 0
Come | Archinard | CAD | 1A | 1 | 0 | 3A | 0
Pierre Guillaume | Thomas | PGT | 1A | 3 | 0 | Total | 22
Calixthe | Mattei | CMI | 1A | 2 | 0
Tanguy | Maurin | TMN | 1A | 1 | 0
LAS
Michele | Schio | MSO | 1A | 0 | 0
Victor | Hugo | VDO | 1A | 0 | 0
Paul | Charcaluk | PCK | 1A | 0 | 0
Pierre Emmanuel | Ariaux | PAX | 1A | 0 | 0
Arthur | Delort | ADT | 1A | 0 | 0
Martin | Kasinsky | MKI | 1A | 17 | 0
Engine
Thibault | Lassus | TLS | 1A | 2 | 1
Aimery | Sauliere | ASE | 1A | 2 | 0
Idriss | Gouhaga | IGH | 1A | 0 | 0
Ghassen | Lassoued | GLD | 1A | 4 | 0
Mathieu | Jacquet | MJT | 1A | 2 | 2
Erwan | Benkara | EBA | 1A | 1 | 0
Elec
Arthur | Rodriguez | ARZ | 1A | 6 | 4
Corentin | Lepais | CLS | 1A | 6 | 0
Bruno | Morera | BMA | 1A | 6 | 0
Romain | Martin | RMN | 1A | 2 | 0
Martin | Gomez | MGZ | 1A | 3 | 0

## FSAE
FSAE |  |  |  | Scale |  | Date du jour |  |  | Week
NGO_ARZ |  |  |  | 0 |  | 2017-07-30 |  |  | 31
100
[5 empty] | W 8 | W 9 | W 10 | W 11 | W 12 | W 13 | W 14 | W 15 | W 16 | W 17 | W 18 | W 19 | W 20 | W 21 | W 22 | W 23 | W 24 | W 25 | W 26 | W 27 | W 28 | W 29 | W 30 | W 31
Task | Task | First day | Final day | Advancement
FSN
Electronic Throttle Contrôle | ETC |  | 2019-03-15 | 100 | W 11: 100
Impact Attenuator Data | IAD |  | 2019-03-15 | 0 | W 11: 0
Structural Equivalency 3D Model | SE3D |  | 2019-03-15 | 50 | W 11: 50
Structural Equivalency Spreaddheet | SES |  | 2019-03-15 | 50 | W 11: 50
Business Plan Executive Summary | BPES |  | 2019-05-31 | 0 | W 22: 0
Design Spec Sheet | DSS |  | 2019-05-31 | 0 | W 22: 0
Engineering Design Report | EDR |  | 2019-05-31 | 0 | W 22: 0
Magazine Uploads | MU |  | 2019-05-31 | 0 | W 22: 0
Fuel Type Order | FTO |  | 2019-06-14 | 0 | W 24: 0
Team Member Registration Form | TMRF |  | 2019-06-14 | 0 | W 24: 0
Vehicle Status Video | VSV |  | 2019-06-14 | 0 | W 24: 0
Cost Report Ducuments | CRD |  | 2019-06-14 | 0 | W 24: 0
Vehicle arrival on site |  | 2019-07-05 | 2019-07-07 | 0 | W 27: 0; W 28: 0
Vehicle departure |  |  | 2019-07-12 | 0 | W 28: 0
FSATA
Electronic Throttle Contrôle | ETC |  | 2019-03-08 | 100 | W 10: 100
Camping booking form |  |  | 2019-03-08 | 0 | W 10: 0
Preliminary team member list |  |  | 2019-03-08 | 100 | W 10: 100
Fuel system data |  |  | 2019-03-08 | 100 | W 10: 100
Structural Equivalency Spreaddheet | SES |  | 2019-03-20 | 0 | W 12: 0
Camping confirmation and payment |  |  | 2019-04-05 | 0 | W 14: 0
Final team member list |  |  | 2019-05-10 | 0 | W 19: 0
Impact Attenuator Data | IAD |  | 2019-05-31 | 0 | W 22: 0
Engineering Design Report | EDR |  | 2019-06-06 | 0 | W 23: 0
Design Spec Sheet | DSS |  | 2019-06-06 | 0 | W 23: 0
Executive Summary |  |  | 2019-06-06 | 0 | W 23: 0
E-Cost Report |  |  | 2019-06-21 | 0 | W 25: 0
E_BOM |  |  | 2019-06-21 | 0 | W 25: 0
Vehicle Status Video | VSV |  | 2019-06-26 | 0 | W 26: 0
Change of Faculty Advisor |  |  | 2019-06-28 | 0 | W 26: 0
Vehicle Shipping and Delivery |  |  | 2017-07-23 | 0 | W 30: 0
Vehicle Shipping and Collection |  |  | 2019-07-30 | 0 | W 31: 0
Formulas:
Week = WEEKNUM([Date du jour])

## Team
Team |  |  | Scale |  | Date du jour |  |  | Week
MJT_ARZ_TLS |  |  | 0 |  | 2019-03-11 |  |  | 11
100
|  |  |  | W 8 |  | W 9 |  | W 10 |  | W 11 |  | W 12
Task | Trigramm | Trigramm | Advancement
RollOut
Communication flyer | ARZ |  | 75 |  | 50 | 75 | 75 | 75 | 75 | 75
Press file | TLS | [5 empty] | 50 | 95 | 95 | 95
Force alpha +
P12P | MJT | ARZ | 100 |  |  |  | 100
Profession de foi | MJT | ARZ | 100 |  |  |  | 100
Create Slack | [9 empty] | 0 | 0
Create Git | [9 empty] | 0 | 0
Create EPSABox | [9 empty] | 50 | 50
Create Brainstorming slides | [9 empty] | 0 | 0
Logiciels
10Po creation ??? | ARZ | [8 empty] | 0
Formulas:
Week = WEEKNUM([Date du jour])

## Frame
Frame |  |  | Scale |  | Date du jour |  |  | Week
CMI_PTS_TMN_CAD_CSN |  |  | 0 |  | 2019-03-07 |  |  | 10
100
|  |  |  | W 8 |  | W 9 |  | W 10 |  | W 11 |  | W 12
Task | Trigramm | Trigramm | Advancement
Aerodynamics
Read aero rules
Find way to fix aero kit |  |  | 25 |  |  |  | 25
Try to integrate a front spoiler | CMI |  | 25 |  |  |  | 25
Try to integrate a rear spoiler | PTS |  | 25 |  |  |  | 25
Try to integrate a diffuser | TMN |  | 25 |  |  |  | 25
Ergonomics
Read ergonomics rules | PGT
Test with atomix | PGT |  | 0 |  |  |  |  | 0
See with former pilots | PGT | [6 empty] | 0 | 0 | 0 | 0
Frame
Read frame rules | CMI
Pushbar
Finish the pushbar design | CAD | TLS | 20 |  |  |  |  | 20 | 20 | 20 | 20 | 20 | 20
Formulas:
Week = WEEKNUM([Date du jour])

## LAS
LAS |  |  | Scale | Date du jour | Date du jour |  | Week
MKI_PAX_VDO_PCK_MSO_ADT |  |  | 0 |  | 2019-03-07 |  | 10
100
|  |  |  | W 8 |  | W 9 | W 10 |  | W 11 |  | W 12
Task | Trigramm | Trigramm | Advancement
Tyre data
Find tyre data | MKI | [6 empty] | 0 | 0 | 0
Models and correlation
Longitudinal acceleration model (2 wheels) | MKI |  | 50 |  |  |  | 50 | 50 | 50 | 50
Longitudinal acceleration model (4 wheels) | MKI |  | 0 | [7 empty] | 0 | 0
How to use Optimus data to improve the model (sensors, ...) | MKI |  | 0
Brake model (2 wheels) | MKI |  | 50 |  |  |  | 50 | 50 | 50 | 50
Brake model (4 wheels) | MKI |  | 0 | [7 empty] | 0 | 0
How to use Optimus data to improve the model (brake pressure sensors, ...) | MKI |  | 0
Lateral acceleration model (2 wheels) | MKI |  | 0
Lateral acceleration model (4 wheels) | MKI |  | 0
How to use Optimus data to improve the model (sensors, ...) | MKI |  | 0
Skid pad model (2 wheels) | MKI |  | 0
Skid pad model (4 wheels) | MKI |  | 0
How to use Optimus data to improve the model (acceleration sensors, tyre temp ? ...) | MKI |  | 0
Maximum turn radius | MKI
Minimum turn radius | MKI
Anti roll bar model | MKI |  | 0
How to use Optimus data to improve the model (roll data with and without anti-roll bar, ...) | MKI |  | 0
Formulas:
Week = WEEKNUM([Date du jour])

## Engine
Engine |  |  | Scale |  | Date du jour |  | Week
MJT_TLS_EBA_IGH_ASE |  |  | 0 |  | 2019-03-07 |  | 10
100
|  |  |  | W 8 |  | W9 | W 10 |  | W 11 |  | W 12
Task | Trigramm | Trigramm | Advancement
History
Steal 6zer | MJT | TLS | 0
General Model
Optimum lap | IGH | [5 empty] | 20 | 20 | 20
Air intake
Measure intake manufolds | TLS |  | 0
Measure exhaust manufolds | TLS |  | 0
Exhaust system
Measure intake manufolds | MJT |  | 0
Measure exhaust manufolds | MJT |  | 0
Cooling
Thermodynamic and thermal model | ASE |  | 0 |  |  |  | 10 | 10
Surface and Fan consumption | ASE | [5 empty] | 10 | 10
Fuel system
Look at what is done in Nascar | GLD | [5 empty] | 0 | 0
See how we can do it with our rules | GLD | [7 empty] | 0 | 0
Refueling | GLD | [9 empty] | 0 | 0
Under and overpressure issues | GLD
Secondary transmission
Load cases on excentric carriers | EBA |  | 0 | [5 empty] | 0 | 0 | 0 | 0
Formulas:
Week = WEEKNUM([Date du jour])

## Elec
Electronic |  |  | Scale |  | Date du jour |  |  | Week
ARZ_CLS_BMA_MGZ_RMN |  |  | 0 |  | 2019-03-07 |  |  | 10
100
|  |  |  | W 8 |  | W9 |  | W 10 |  | W 11 |  | W 12
Task | Trigramm | Trigramm | Advancement
Shifter
Finish the shifter soft | BMA | CLS | 100 |  |  |  | 100
Connect to the shifter | BMA | CLS | [5 empty] | 0 | 0
Finish 2 rear cards | BMA | CLS | [5 empty] | 0 | 0
Test the shifter soft with atomix | BMA | CLS | 0 | [6 empty] | 0 | 0
BSPD | BMA | CLS | [5 empty] | 0
Pro & Cons pneumatic shifter | BMA | CLS
Front card
Pinout File | [7 empty] | 20 | 20
Program the error display | MGZ |  | 100 |  |  |  | 100
Test error display | ARZ | [6 empty] | 0 | 0
Finish the comments of the soft | MGZ |  | 50 |  |  |  | 50 | 50 | 50
Test the final program | ARZ |  | 50 | [6 empty] | 50 | 50
Finish cards x2 | [7 empty] | 30 | 30 | 30 | 30
Test handmade cards | [8 empty] | 10 | 10 | 10
Dashboard
Finish Rapidharness | RMN |  | 50 |  |  |  |  | 50 | 50 | 50 | 50
Test 2nd dashboard | ARZ |  | 100 |  |  |  | 100
Steering Wheel
Paddle shifter design | RMN
Sensors
Contact FLE for sensor callibration | ARZ |  | 0 | [6 empty] | 0 | 0
Change the connectors | ARZ |  | 0
Select sensors with each departements | ARZ | [8 empty] | 0 | 0 | 0 | 0
Create the code to send the sensors data on the CAN | MGZ |  | 0 | [8 empty] | 0 | 0
Formulas:
Week = WEEKNUM([Date du jour])